## 1. Executive Summary
MONEY CARD PLATFORM — COMPREHENSIVE ROADMAP (3-4 WEEKS TIMELINE)
Source of Truth: M0 V10 Frozen Contract • Standard: 8 Productive Hours / Day • 5 Days / Week • Horizon: 3 to 4 Calendar Weeks
1. Overall Project Status & Timeline Summary (3-4 Weeks Aligned)
Platform / Track | Lead Developer | Current Architecture Status | Completed Work (Days) | Completed Work (Hours) | Remaining Work (Days) | Remaining Work (Hours) | Total Effort (Days) | Total Effort (Hours) | Progress (%)
Backend API (Node.js / Prisma / PostgreSQL) | Developer 2 | Starting from Scratch (Paced for 3-4 Weeks) | 0 | 0 | 15 | 120 | 15 | 120 | 0.0%
Web Admin Frontend (React / TypeScript / Vite) | Developer 1 | 91.3% Complete (M1–M11 Verified) | 21 | 168 | 1 | 8 | 22 | 176 | 95.5%
Staff Mobile App (Flutter Native / Riverpod) | Developer 1 | 100% Client Ready (M13–M17, M19 Done) | 11 | 88 | 1.5 | 12 | 12.5 | 100 | 88.0%
Joint Post-Merge Integration & Production Release | Dev 1 + Dev 2 | Scheduled Week 4 (Days 16–20) | 0 | 0 | 5 | 40 | 5 | 40 | 0.0%
TOTAL COMBINED PROJECT EFFORT | All Tracks | Parallel Execution Schedule
2. Strategic 3-4 Weeks Schedule Alignment Comparison
Comparison Dimension | Aggressive 7-Day Fast-Track (Previous) | Realistic 3-4 Weeks Horizon (Aligned) | Benefits to Engineering & Delivery Quality
Backend Development Duration | 7 Working Days (56 Hours) | 15 Working Days (120 Hours) | Ample time to write robust Prisma models, migrations, indexes, and custom business validation.
Pacing & Daily Workload | 3.0 Milestones / Day (High Risk) | 1.25 to 1.5 Milestones / Day (Sustainable) | Avoids developer burnout, allows thorough local integration testing of all 65 endpoints.
Concurrency & Financial Safety | Basic atomic operations | Full PostgreSQL $transaction locks & Isolation | Guarantees zero negative stock, strict balance idempotency, and audit trail safety.
Joint Integration Window | 3 Working Days (24 Hours) | 5 Working Days (40 Hours) | Full 1-week dedicated buffer for live CORS, PostgreSQL load testing, and Android QR hardware QA.
Total Calendar Horizon | 2 Calendar Weeks (10 Days) | 4 Calendar Weeks (20 Working Days) | Delivers an enterprise-grade, thoroughly tested system ready for immediate live production launch.

## 2. Dev 2 (Backend Roadmap)
DEVELOPER 2 (BACKEND) — 3-4 WEEKS IMPLEMENTATION ROADMAP
Stack: Node.js • TypeScript • Express • Prisma ORM • PostgreSQL • Target: 20 Milestones / 65 Routes / 120 Hours (15 Working Days)
Milestone | Task & Module Name | Week | Allocated Days | Allocated Hours | Dependencies | M0 V10 Endpoint Scope | Key Technical Deliverables & Architecture Scope | Testing & Verification Criteria
D2-M1 | Backend Foundation, Express & Error Architecture | Week 1 (Day 1) | 0.5 | 4 | None | Global Router | Express TypeScript bootstrap, .env config, Winston logger, M0 V10 {success, data, error} envelope middleware, CORS. | Server boots on port 8080/4000, returns formatted M0 error envelope on 404/500.
D2-M2 | PostgreSQL Database Schema & Prisma ORM Setup | Week 1 (Day 1-2) | 0.75 | 6 | D2-M1 | DB Migrations | 12 Prisma models (Organization, Branch, User, Card, CardSession, Product, InventoryItem, InventoryMovement, Transaction, Plan, PlanRequest, AuditLog). Seed from TEST_DATA.json. | Prisma migrate deploy succeeds, seed script populates demo organizations, branches, and staff.
D2-M3 | Authentication Module & JWT Lifecycle | Week 1 (Day 2) | 0.75 | 6 | D2-M2 | POST /auth/login, POST /auth/refresh, POST /auth/logout, GET /auth/me, POST /auth/forgot-password, POST /auth/reset-password, POST /auth/change-password (7 routes) | Argon2/Bcrypt password hashing, 15m JWT access tokens, 7d refresh tokens with database revocation, getMe enriched with permissions & branches. | Login returns valid tokens, expired access token refreshes seamlessly, logout revokes refresh token.
D2-M4 | Authorization, RBAC & Multi-Tenant Middleware | Week 1 (Day 3) | 0.75 | 6 | D2-M3 | Middleware Layer | Role guards (SUPER_ADMIN, ORG_ADMIN, STAFF), 20 granular AppPermission evaluators, automatic tenant organization & assigned branch isolation filter. | Unauthorized requests return 401, missing permission returns 403 FORBIDDEN, cross-org access blocked.
D2-M5 | Organizations Management APIs (Super Admin) | Week 1 (Day 4) | 0.75 | 6 | D2-M4 | GET /organizations, POST /organizations, GET /organizations/:id, PUT /organizations/:id, DELETE /organizations/:id (5 routes) | Super Admin tenant listing, tenant provisioning with default branch & admin creation, status updates with cascading deactivation. | Super Admin can create tenant, edit status; regular staff cannot access /organizations.
D2-M6 | Subscription Plans, Limits & Quota Overrides | Week 1 (Day 5) | 0.75 | 6 | D2-M5 | GET /plans, POST /plans, PUT /plans/:id, GET /plans/requests, POST /plans/requests, POST /plans/requests/:id/approve, POST /plans/requests/:id/reject, PUT /organizations/:id/limits (8 routes) | Global pricing plans (NO transaction limits), custom org quota overrides (card/branch limits), plan change approval workflow. | Plan limits enforced when org exceeds max branches/cards; approval upgrades tenant plan.
D2-M7 | Branches & Staff Management APIs | Week 2 (Day 6) | 0.75 | 6 | D2-M4 | GET /branches, POST /branches, GET /branches/:id, PUT /branches/:id, GET /staff, POST /staff, GET /staff/:id, PUT /staff/:id, DELETE /staff/:id (9 routes) | Branch CRUD with org isolation, Staff CRUD, branch assignments replacement, permission array replacement, branch count limit checks. | Staff assigned to Branch 1 cannot access Branch 2; branch creation respects plan limits.
D2-M8 | Card Inventory & Dual QR Resolution Engine | Week 2 (Day 7) | 0.75 | 6 | D2-M7 | GET /cards, POST /cards, GET /cards/:id, POST /cards/resolve, POST /cards/:id/block, POST /cards/:id/unblock (6 routes) | Authoritative card inventory, AVAILABLE state on import, opaque qrToken mapping, POST /cards/resolve with active session enrichment, block/unblock. | QR resolve returns 404 for unknown QR, returns card + active session for valid QR, block prevents operations.
D2-M9 | Card Sessions Lifecycle & Balance Management | Week 2 (Day 8) | 0.75 | 6 | D2-M8 | GET /card-sessions, POST /card-sessions, GET /card-sessions/:id (3 routes) | Session creation on AVAILABLE card (transitions card to ACTIVE), active session list filtered by branch, session detail with balance. | Cannot create session on ACTIVE/BLOCKED card; active session count dynamically accurate.
D2-M10 | Product Catalog Management APIs | Week 2 (Day 9) | 0.75 | 6 | D2-M7 | GET /products, POST /products, GET /products/:id, PUT /products/:id, DELETE /products/:id (5 routes) | Branch product catalog, multi-select category array (List<String>, NO tags), price validation, auto InventoryItem record initialization. | Products correctly scoped to branch; category array saves and filters accurately.
D2-M11 | POS Checkout & Purchase Financials Engine | Week 2 (Day 10) | 1 | 8 | D2-M9, D2-M10 | POST /card-sessions/:id/purchase (1 route) | Atomic Prisma $transaction: server price lookup, balance verification, stock verification, balance deduction, stock decrease, Transaction record. | Insufficient balance returns 400; concurrency test ensures zero double-spending or negative balances.
D2-M12 | Card Recharge & Payment Records | Week 3 (Day 11) | 0.75 | 6 | D2-M9 | POST /card-sessions/:id/recharge (1 route) | Card session top-up with CASH or manual UPI verification reference, atomic balance credit, idempotency reference validation, Transaction record. | Recharge credits session balance immediately; duplicate externalReference is rejected.
D2-M13 | Card Return, Refund & Session Settlement | Week 3 (Day 11-12) | 0.75 | 6 | D2-M11, D2-M12 | POST /card-sessions/:id/return (1 route) | Session settlement: calculates remaining balance, records REFUND transaction, zeroes session balance, marks session SETTLED, resets card to AVAILABLE. | Settled session cannot be reused; card immediately available for re-issuance with ₹0 balance.
D2-M14 | Inventory Stock Control & 3-Column CSV Import | Week 3 (Day 12-13) | 1 | 8 | D2-M10 | GET /inventory, POST /inventory/:id/adjust, GET /inventory/movements, POST /inventory/import-csv, GET /inventory/csv-template (5 routes) | Stock level tracking, manual stock adjustments with audit reason (RESTOCK/ADJUSTMENT), 3-col CSV parser (itemName,category,price) with 2-phase preview & commit. | Stock adjustment logs InventoryMovement; CSV import previews rows and creates products + inventory.
D2-M15 | Real-Time Branch Analytics & Aggregations | Week 3 (Day 13) | 0.75 | 6 | D2-M11, D2-M12 | GET /analytics (1 route) | Aggregated metrics calculation: total revenue, recharge volume, purchase volume, active sessions, peak demand hours, top-selling items. | Analytics metrics match sum of completed transactions for requested branch and date range.
D2-M16 | Formal PDF Reports Engine (Binary Streaming) | Week 3 (Day 14) | 0.75 | 6 | D2-M15 | GET /reports, POST /reports/generate, GET /reports/:id/download (3 routes) | Formal business reports list, asynchronous report generator using PDFKit, binary streaming PDF download conforming to M0 V10. | GET /reports/:id/download returns application/pdf with valid binary PDF content.
D2-M17 | Public Customer User Portal APIs | Week 3 (Day 14) | 0.75 | 6 | D2-M9 | POST /portal/resolve, GET /portal/session, GET /portal/transactions (3 routes) | Public card QR resolution with data masking, temporary portal session token, live card balance lookup, customer transaction receipt history. | Public user can check balance and view digital receipts without staff credentials.
D2-M18 | System Audit Logging & Interceptors | Week 3 (Day 15) | 0.75 | 6 | D2-M4 | GET /audit-logs (1 route) | Automated Prisma middleware logging all auth events, card state transitions, financial transactions, staff changes, and plan modifications. | Sensitive operations automatically log actor ID, action, entity, and timestamp to AuditLog table.
D2-M19 | API Contract Parity Verification (All 65 Routes) | Week 3 (Day 15) | 0.75 | 6 | D2-M1 to D2-M18 | Full 65 Routes | Rigorous schema validation verifying every endpoint against MONEY_CARD_COMPLETE_API_CONTRACT_V10.pdf: envelopes, status codes, query params. | 100% route parity verified; zero schema deviations from M0 V10 specification.
D2-M20 | Postman QA Collection Pass & Handover | Week 3 (Day 15) | 0.75 | 6 | D2-M19 | Postman Suite (65 Requests) | Automated Postman Collection Runner execution covering all 65 endpoints across Super Admin, Org Admin, and Staff roles. | 65/65 Postman assertions pass green (100% success rate); backend certified ready for frontend merge.
DEVELOPER 2 TOTAL (BACKEND TRACK) | All 20 Milestones / 65 Authoritative Routes | Weeks 1 to 3 |  |  | Full Pipeline | 65/65 Endpoints | Complete PostgreSQL & Node.js Production Backend | Postman 100% Pass Certification

## 3. Dev 1 (Web Frontend)
DEVELOPER 1 (WEB FRONTEND) — ROADMAP & STATUS
Stack: React 18 • TypeScript • Vite • Tailwind / Custom CSS • Status: 91.3% Complete (M1–M11 Verified, M12 Pending Backend)
Milestone | Task Name | Time (Days) | Time (Hours) | Current Status | Key Scope & Technical Deliverables
M1 | Foundation & Design System | 2 | 16 | COMPLETED | Design tokens, dark/light themes, responsive navigation, top header, breadcrumbs, standard UI kit.
M2 | Authentication & RBAC Suite | 2 | 16 | COMPLETED | Login screens, forgot password modal (neutral response), reset password, change password, profile dropdown, role guards.
M3 | Cards Management & Issue | 2 | 16 | COMPLETED | Card list, QR barcode viewer modal, manual card creation, CSV template download & import, status filter with Available count.
M4 | Sessions Management | 1.75 | 14 | COMPLETED | Active session dashboard, session issuance, branch filtering, live session balance indicators, session details modal.
M5 | POS Terminal & Products | 2.25 | 18 | COMPLETED | POS checkout cart, product catalog grid, search/filter, multi-select category tags (string[]), price calculation (no tags).
M6 | Payments, Recharge & Refunds | 1.5 | 12 | COMPLETED | Cash top-up modal, manual UPI verification modal, digital receipt modal, session return/refund modal with settlement confirmation.
M7 | Inventory & 3-Column CSV | 2 | 16 | COMPLETED | Live inventory table, stock adjustments, low stock badges, 3-column CSV template download, branch 2-phase preview & commit.
M8 | Analytics & Peak Demand | 2 | 16 | COMPLETED | Real-time analytics dashboard, branch performance comparison table, peak hours traffic charts, hourly breakdown, PDF export.
M9 | Offline Resilience & Mock Store | 1.5 | 12 | COMPLETED | In-memory mock database store, realistic latency simulation, localStorage state persistence, reset store utility.
M10 | Admin Controls & Subscriptions | 2.25 | 18 | COMPLETED | Super Admin tenant org manager, plan comparison matrix, plan upgrade/downgrade request form, limit overrides manager.
M11 | Web Polish & Contract QA | 1.75 | 14 | COMPLETED | Automated contract test runner integration, 58/58 test pass verification, zero TypeScript errors, production build optimization.
M12 | Web Real Backend Integration | 1 | 8 | REMAINING (Week 4) | Switch .env VITE_USE_MOCK_API=false to point to live Node.js server (http://localhost:4000/api/v1), smoke test all 65 routes.

## 4. Dev 1 (Flutter Staff App)
DEVELOPER 1 (FLUTTER STAFF MOBILE APP) — ROADMAP & STATUS
Stack: Flutter 3.x • Dart • Riverpod 2.6 • Dio • Mobile Scanner • EscPos Thermal • Status: M13–M17, M19 Completed (118 Tests Passing)
Milestone | Task Name | Time (Days) | Time (Hours) | Current Status | Key Scope & Technical Deliverables
M13 | Flutter Foundation & Architecture | 1.75 | 14 | COMPLETED | Light theme, Dio network client with Auth/Error/Mock interceptors, SecureStorage token manager, AppRouter, AppShell.
M14 | Staff Authentication & Permissions | 1.5 | 12 | COMPLETED | Login screen, token refresh handling, branch switcher, PermissionGuard, role/permission providers, auth service.
M15 | Staff Cards & QR Operations | 2.25 | 18 | COMPLETED | Camera QR scanner (QRScannerView), manual card entry fallback, QR resolve (POST /cards/resolve), card list, Home active session counter.
M16 | Payments, POS Checkout & Return | 2.75 | 22 | COMPLETED | Cash recharge screen, manual UPI verification screen (store physical QR used), POS catalog cart (POSCartProvider), return card & refund screen.
M17 | Inventory & Shift Analytics | 2 | 16 | COMPLETED | Inventory screen with live stock, quick stock adjustment, AddProductScreen with multi-category selector, staff AnalyticsScreen with volume cards.
M18 | Real Backend Integration & QA Audit | 1 | 8 | AUDIT READY (Week 4) | Integration readiness audit passed (FLUTTER_REAL_API_INTEGRATION_AUDIT.md). Switch AppConfig.apiMode = real to point to live backend.
M19 | Hardware, Scanner & Mock QR Hardening | 1 | 8 | COMPLETED | Camera torch toggle, scan vibration feedback, ESC/POS thermal receipt formatting (58mm/80mm), physical camera Mock QR display.
M20 | Android Production QA & Release | 0.5 | 4 | REMAINING (Week 4) | Release keystore signing, ProGuard rules, Android APK/AAB build generation, offline network error handling validation.

## 5. Master Daily Schedule (3-4W)
MASTER PARALLEL DAILY SCHEDULE — 4 WEEKS (20 WORKING DAYS)
Coordinated Multi-Track Sprint Plan: Backend Build (Weeks 1–3) + Joint Integration & Release QA (Week 4)
Calendar Timeline | Developer 2 (Backend Track) | Developer 1 (Web & Flutter Tracks) | Daily Target Deliverable & Milestone Output | Sign-Off Status
Week 1 • Day 1 | D2-M1: Express TS Setup & Error Envelope Middleware | Flutter Mock QR Codes Screen & Scanner Validation | Backend server running with global error envelope; Flutter camera test verified. | PLANNED
Week 1 • Day 2 | D2-M2: PostgreSQL Connection & Prisma Schema Models | Web Frontend M1–M6 Contract Review & Mock Sync | 12 Prisma database models created & migrated; seed data loaded. | PLANNED
Week 1 • Day 3 | D2-M3: Authentication Module (JWT, Refresh, Password) | Flutter Hardware Settings & Thermal Printer Hardening | Login, refresh, and logout APIs fully operational with Argon2 hashing. | PLANNED
Week 1 • Day 4 | D2-M4: RBAC & Multi-Tenant Isolation Middleware | Web Frontend M7–M10 Tenancy & RBAC Verification | Role guards and organization/branch tenant scoping active on all routes. | PLANNED
Week 1 • Day 5 | D2-M5: Organizations & D2-M6: Plans Management APIs | Web & Flutter Shared Model Type-Check against M0 V10 | Super Admin tenant listing, provisioning, and global plan limit APIs complete. | PLANNED
Week 2 • Day 6 | D2-M7: Branches & Staff Management CRUD APIs | Flutter Active Sessions Dynamic Calculation QA | Branch CRUD, staff permissions replacement, and branch limit validation live. | PLANNED
Week 2 • Day 7 | D2-M8: Card Inventory & Dual QR Resolution APIs | Flutter Card Resolver & QR Debouncing Verification | Authoritative card inventory with AVAILABLE status & QR token resolution live. | PLANNED
Week 2 • Day 8 | D2-M9: Card Sessions Lifecycle & Active Balances | Flutter Issue Card Session Creation Flow Testing | Session creation on available cards & active session list endpoints live. | PLANNED
Week 2 • Day 9 | D2-M10: Product Catalog APIs (Multi-Category Array) | Web POS Catalog Multi-Select Category Verification | Branch product CRUD with category arrays (zero tags) & auto-inventory init. | PLANNED
Week 2 • Day 10 | D2-M11: POS Purchase Engine ($transaction Locks) | Flutter POS Checkout Cart & Decimal Price Verification | Atomic purchase execution with server price lookup & stock deduction live. | PLANNED
Week 3 • Day 11 | D2-M12: Recharge & D2-M13: Session Refund/Return | Flutter Recharge & Return Settlement Dialogs QA | CASH/UPI wallet recharge and session refund/settlement transactions live. | PLANNED
Week 3 • Day 12 | D2-M14: Inventory Stock Adjustments & CSV Import | Web 3-Column CSV Import & Live Inventory Testing | Inventory adjustments with audit logs & 3-column CSV import engine live. | PLANNED
Week 3 • Day 13 | D2-M15: Real-Time Analytics & Aggregated Metrics | Web & Flutter Analytics Volume Cards Parity Check | Real-time revenue, recharge, purchase, and peak hour analytics live. | PLANNED
Week 3 • Day 14 | D2-M16: Reports Engine (PDF) & D2-M17: Customer Portal | Flutter Digital Receipt Preview Monospace QA | Binary PDF streaming reports download & public customer portal APIs live. | PLANNED
Week 3 • Day 15 | D2-M18: Audit Logging & D2-M19/M20: Postman QA Pass | Full 65-Route Contract Verification Sign-Off | All 65 routes passing Postman Collection 100%; BACKEND DELIVERED FOR MERGE! | MILESTONE GATE
Week 4 • Day 16 | Joint Backend Support: CORS, Network Latency, DB Logs | Web M12: Real API Integration (65 Routes E2E QA) | Web Admin Frontend 100% connected to live backend & PostgreSQL. | JOINT QA
Week 4 • Day 17 | Joint Backend Support: JWT Refresh & Session Monitoring | Flutter M18: Real API Integration & Live POS QA | Flutter Staff App 100% connected to live backend; live card issuing verified. | JOINT QA
Week 4 • Day 18 | Joint Concurrency & Multi-Tenant Boundary Stress Testing | Simultaneous Multi-Branch Purchase & Recharge Testing | Database locks verified under concurrent purchasing; zero data leakage. | JOINT QA
Week 4 • Day 19 | Final Security Audit, Input Sanitization & SQL Guard | Flutter M19 Hardware & ESC/POS Thermal Printing Live Test | Hardware printers and physical scanner tested against live database. | JOINT QA
Week 4 • Day 20 | Production Database Migration & Server Deployment | Flutter M20: Keystore Signing & Release APK/AAB Build | FINAL PRODUCTION SIGN-OFF: Web, Mobile, and Backend 100% Live! | FINAL RELEASE

## 6. 65-Route API Matrix
M0 V10 COMPLETE 65-ROUTE AUTHORITATIVE API SPECIFICATION MATRIX
Frozen Shared System Contract • Standard: /api/v1 Base Path • Envelope: {success: boolean, data: object, error: object}
Route # | Module Domain | HTTP Method | API Endpoint Path | Required Role / Permission | Request Payload / Parameters | Authoritative M0 V10 Response
1 | Authentication | POST | /api/v1/auth/login | Public | {email, password} | {accessToken, refreshToken, user: {id, email, role, permissions}}
2 | Authentication | POST | /api/v1/auth/refresh | Public (Bearer Refresh) | {refreshToken} | {accessToken, refreshToken}
3 | Authentication | POST | /api/v1/auth/logout | Authenticated | None | {message: 'Logged out successfully'}
4 | Authentication | GET | /api/v1/auth/me | Authenticated | None | {user: {id, email, name, role, permissions, assignedBranchIds}}
5 | Authentication | POST | /api/v1/auth/forgot-password | Public | {email} | {message: 'Password reset link sent'}
6 | Authentication | POST | /api/v1/auth/reset-password | Public | {token, newPassword} | {message: 'Password reset successful'}
7 | Authentication | POST | /api/v1/auth/change-password | Authenticated | {currentPassword, newPassword} | {message: 'Password changed successfully'}
8 | Organizations | GET | /api/v1/organizations | SUPER_ADMIN | ?status, ?search, ?page, ?limit | {items: [{id, name, status, planId, branchCount}]}
9 | Organizations | POST | /api/v1/organizations | SUPER_ADMIN | {name, email, planId, adminName, adminPassword} | {organization: {id, name, status}, admin: {id, email}}
10 | Organizations | GET | /api/v1/organizations/:id | SUPER_ADMIN / ORG_ADMIN | Path: id | {id, name, status, planId, limits, createdAt}
11 | Organizations | PUT | /api/v1/organizations/:id | SUPER_ADMIN | Path: id, {name, status, planId} | {id, name, status, updatedAt}
12 | Organizations | DELETE | /api/v1/organizations/:id | SUPER_ADMIN | Path: id | {message: 'Organization deactivated'}
13 | Plans & Subscriptions | GET | /api/v1/plans | Authenticated | None | [{id, name, price, maxBranches, maxCards, features}]
14 | Plans & Subscriptions | POST | /api/v1/plans | SUPER_ADMIN | {name, price, maxBranches, maxCards, features} | {id, name, price, maxBranches, maxCards}
15 | Plans & Subscriptions | PUT | /api/v1/plans/:id | SUPER_ADMIN | Path: id, {name, price, maxBranches, maxCards} | {id, name, price, updatedAt}
16 | Plans & Subscriptions | GET | /api/v1/plans/requests | SUPER_ADMIN | ?status, ?page, ?limit | {items: [{id, organizationId, requestedPlanId, status}]}
17 | Plans & Subscriptions | POST | /api/v1/plans/requests | ORG_ADMIN | {requestedPlanId, reason} | {id, organizationId, status: 'PENDING'}
18 | Plans & Subscriptions | POST | /api/v1/plans/requests/:id/approve | SUPER_ADMIN | Path: id | {id, status: 'APPROVED', effectivePlanId}
19 | Plans & Subscriptions | POST | /api/v1/plans/requests/:id/reject | SUPER_ADMIN | Path: id, {reason} | {id, status: 'REJECTED', reason}
20 | Plans & Subscriptions | PUT | /api/v1/organizations/:id/limits | SUPER_ADMIN | Path: id, {maxBranches, maxCards} | {organizationId, customLimits: {maxBranches, maxCards}}
21 | Branches | GET | /api/v1/branches | Authenticated | ?organizationId | [{id, organizationId, name, address, phone, isActive}]
22 | Branches | POST | /api/v1/branches | ORG_ADMIN (BRANCH_MANAGE) | {name, address, phone} | {id, organizationId, name, isActive: true}
23 | Branches | GET | /api/v1/branches/:id | Authenticated | Path: id | {id, organizationId, name, address, phone, isActive}
24 | Branches | PUT | /api/v1/branches/:id | ORG_ADMIN (BRANCH_MANAGE) | Path: id, {name, address, phone, isActive} | {id, name, address, isActive, updatedAt}
25 | Staff Management | GET | /api/v1/staff | ORG_ADMIN (STAFF_VIEW) | ?branchId, ?page, ?limit | {items: [{id, name, email, role, permissions, assignedBranchIds}]}
26 | Staff Management | POST | /api/v1/staff | ORG_ADMIN (STAFF_MANAGE) | {name, email, password, assignedBranchIds, permissions} | {id, name, email, role: 'STAFF'}
27 | Staff Management | GET | /api/v1/staff/:id | ORG_ADMIN (STAFF_VIEW) | Path: id | {id, name, email, permissions, assignedBranchIds}
28 | Staff Management | PUT | /api/v1/staff/:id | ORG_ADMIN (STAFF_MANAGE) | Path: id, {name, assignedBranchIds, permissions, isActive} | {id, name, permissions, updatedAt}
29 | Staff Management | DELETE | /api/v1/staff/:id | ORG_ADMIN (STAFF_MANAGE) | Path: id | {message: 'Staff user deactivated'}
30 | Cards & Inventory | GET | /api/v1/cards | STAFF (CARD_VIEW) | ?branchId, ?status, ?search, ?page, ?limit | {items: [{id, qrToken, physicalCardNumber, status, currentBranchId}]}
31 | Cards & Inventory | POST | /api/v1/cards | STAFF (CARD_ISSUE) | {physicalCardNumber, branchId} | {id, qrToken, physicalCardNumber, status: 'AVAILABLE'}
32 | Cards & Inventory | GET | /api/v1/cards/:id | STAFF (CARD_VIEW) | Path: id | {id, qrToken, physicalCardNumber, status, currentBranchId}
33 | Cards & Inventory | POST | /api/v1/cards/resolve | STAFF (CARD_VIEW) | {qrToken} | {card: {id, physicalCardNumber, status}, session: {id, balance}}
34 | Cards & Inventory | POST | /api/v1/cards/:id/block | STAFF (CARD_BLOCK) | Path: id, {reason} | {id, status: 'BLOCKED', blockReason}
35 | Cards & Inventory | POST | /api/v1/cards/:id/unblock | STAFF (CARD_UNBLOCK) | Path: id | {id, status: 'AVAILABLE'}
36 | Card Sessions | GET | /api/v1/card-sessions | STAFF (SESSION_VIEW) | ?branchId, ?status, ?page, ?limit | {items: [{id, cardId, physicalCardNumber, branchId, status, balance}]}
37 | Card Sessions | POST | /api/v1/card-sessions | STAFF (SESSION_CREATE) | {cardId, branchId} | {id, cardId, branchId, status: 'ACTIVE', balance: 0.0}
38 | Card Sessions | GET | /api/v1/card-sessions/:id | STAFF (SESSION_VIEW) | Path: id | {id, cardId, physicalCardNumber, branchId, status, balance, startedAt}
39 | Card Sessions | POST | /api/v1/card-sessions/:id/purchase | STAFF (PURCHASE) | Path: id, {items: [{productId, quantity}]} | {transactionId, amount, balance, status: 'SUCCESS'}
40 | Card Sessions | POST | /api/v1/card-sessions/:id/recharge | STAFF (RECHARGE) | Path: id, {amount, paymentMethod, externalReference} | {transactionId, amount, balance, paymentMethod, status: 'SUCCESS'}
41 | Card Sessions | POST | /api/v1/card-sessions/:id/return | STAFF (REFUND) | Path: id | {sessionId, refundedAmount, sessionStatus: 'SETTLED', cardStatus: 'AVAILABLE'}
42 | Products Catalog | GET | /api/v1/products | STAFF (PRODUCT_VIEW) | ?branchId, ?category, ?status, ?page, ?limit | {items: [{id, branchId, itemName, category: [], price, status}]}
43 | Products Catalog | POST | /api/v1/products | ORG_ADMIN (PRODUCT_MANAGE) | {branchId, itemName, category: [], price, status} | {id, branchId, itemName, category, price, status: 'ACTIVE'}
44 | Products Catalog | GET | /api/v1/products/:id | STAFF (PRODUCT_VIEW) | Path: id | {id, branchId, itemName, category: [], price, status}
45 | Products Catalog | PUT | /api/v1/products/:id | ORG_ADMIN (PRODUCT_MANAGE) | Path: id, {itemName, category: [], price, status} | {id, itemName, category, price, status, updatedAt}
46 | Products Catalog | DELETE | /api/v1/products/:id | ORG_ADMIN (PRODUCT_MANAGE) | Path: id | {message: 'Product deleted'}
47 | Inventory Control | GET | /api/v1/inventory | STAFF (INVENTORY_VIEW) | ?branchId, ?search, ?status, ?page, ?limit | {items: [{id, productId, productName, branchId, currentStock, status}]}
48 | Inventory Control | POST | /api/v1/inventory/:id/adjust | STAFF (INVENTORY_MANAGE) | Path: id, {adjustment, reason} | {id, productId, currentStock, status, updatedAt}
49 | Inventory Control | GET | /api/v1/inventory/movements | STAFF (INVENTORY_VIEW) | ?branchId, ?inventoryId, ?limit | {items: [{id, inventoryId, productName, type, quantity, reason}]}
50 | Inventory Control | POST | /api/v1/inventory/import-csv | ORG_ADMIN (INVENTORY_MANAGE) | Multipart form-data: file (.csv), ?commit=true/false | {totalRows, validRows, invalidRows, preview: [], committed: boolean}
51 | Inventory Control | GET | /api/v1/inventory/csv-template | Authenticated | None | CSV file attachment (itemName,category,price)
52 | Analytics & Metrics | GET | /api/v1/analytics | STAFF (VIEW_ANALYTICS) | ?branchId, ?range (today, week, month) | {branchPerformance: [{branchId, totalRevenue, rechargeRevenue, purchases}]}
53 | Analytics & Metrics | GET | /api/v1/analytics/demand | STAFF (VIEW_ANALYTICS) | ?branchId, ?range | {topProducts: [{productId, itemName, quantitySold, revenue}]}
54 | Reports Engine | GET | /api/v1/reports | ORG_ADMIN (VIEW_REPORTS) | ?branchId, ?type, ?page, ?limit | {items: [{id, branchId, title, type, dateRange, status}]}
55 | Reports Engine | POST | /api/v1/reports/generate | ORG_ADMIN (VIEW_REPORTS) | {branchId, type, startDate, endDate} | {reportId, status: 'GENERATING'}
56 | Reports Engine | GET | /api/v1/reports/:id/download | ORG_ADMIN (VIEW_REPORTS) | Path: id | Binary PDF file attachment (application/pdf)
57 | Customer Portal | POST | /api/v1/portal/resolve | Public | {qrToken} | {portalToken, maskedCardNumber, status}
58 | Customer Portal | GET | /api/v1/portal/session | Public (Portal Token) | Header: X-Portal-Token | {cardId, activeBalance, status, sessionStartedAt}
59 | Customer Portal | GET | /api/v1/portal/transactions | Public (Portal Token) | Header: X-Portal-Token | {transactions: [{id, type, amount, date, receipt}]}
60 | Audit System | GET | /api/v1/audit-logs | ORG_ADMIN (AUDIT_VIEW) | ?branchId, ?action, ?page, ?limit | {items: [{id, userId, userName, action, entity, timestamp}]}
61 | Audit System | GET | /api/v1/audit-logs/:id | ORG_ADMIN (AUDIT_VIEW) | Path: id | {id, userId, action, entity, details: {}, timestamp}
62 | System & Health | GET | /api/v1/health | Public | None | {status: 'OK', timestamp, database: 'CONNECTED'}
63 | System & Health | GET | /api/v1/version | Public | None | {version: '1.0.0', contract: 'M0_V10_FROZEN'}
64 | System & Health | GET | /api/v1/metrics | SUPER_ADMIN | None | {activeConnections, memoryUsage, uptime}
65 | System & Health | POST | /api/v1/system/seed-reset | SUPER_ADMIN (Dev Only) | {confirm: 'RESET_CONFIRM'} | {message: 'Database re-seeded from TEST_DATA.json'}